## Team Meeting 2
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Member 6 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Jethro Phuah | Lam Zhi Fah | Alicia Chua | Shannon Tan | Shaun Ong | Sim Hao | Ernest Ang
Team member's mood during the this week's meeting: |  |  | Happy | Depressed | Sad | Depressed | Excited | Excited | Happy
1 | Complete Project Plan Report | Task Quality Evaluation (After Task Completed) | 9 | 9 | 8 | 8 | 10 | 8 | 8 | 8.2857 | 7.1429 | 1.5714 | Shaun Ong | Zhi Fah, Sim Hao | Through Discussion | Yes | 5 | Happy | 8.5714
| Estimated Task Priority（0-10） |  | 9 | 9 | 8 | 9 | 8 | 7 | 8
| Estimated Task Difficulty（0-10） |  | 7 | 7 | 8 | 9 | 7 | 7 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 2 | 3 | 1 | 2 | 1
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 10 | 10 | 8 | 9 | 8
2 | Complete Risk Management Plan | Task Quality Evaluation (After Task Completed) | 9 | 8 | 8 | 8 | 9 | 8 | 9 | 9.2857 | 9.1429 | 4.4286 | Jethro Phuah | Ernest, Shannon, Alicia | Through Discussion | Yes | 4 | Neutral | 8.4286
| Estimated Task Priority（0-10） |  | 10 | 9 | 10 | 8 | 9 | 9 | 10
| Estimated Task Difficulty（0-10） |  | 10 | 10 | 10 | 8 | 9 | 8 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 6 | 5 | 4 | 5 | 3 | 4
| Team Member's Confidence about the Task (0-10) |  | 7 | 7 | 6 | 8 | 9 | 6 | 7
3 | Development of App Prototype (Admin and User UI) | Task Quality Evaluation (After Task Completed) | 9 | 10 | 7 | 8 | 8 | 9 | 8 | 4.8571 | 4.7143 | 4.7143 | Shannon Tan | Jethro | Through Discussion | Yes | 5 | Happy | 8.4286
| Estimated Task Priority（0-10） |  | 4 | 6 | 6 | 5 | 4 | 5 | 4
| Estimated Task Difficulty（0-10） |  | 5 | 5 | 6 | 3 | 5 | 4 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 6 | 3 | 5 | 4 | 5
| Team Member's Confidence about the Task (0-10) |  | 8 | 6 | 7 | 8 | 7 | 6 | 8
4 | Connecting Firebase to application | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 9 | 9 | 10 | 4.1429 | 1.2857 | Shannon Tan | Ernest | Through Discussion | Yes | 1 | Happy | 9.7143
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 5 | 3 | 5 | 4 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 2 | 1 | 1 | 2 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 8 | 9 | 9 | 8 | 9