## Risk Register
No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses / Mitigating Actions | Risk Owners | Probability | Impact | Status
1 | 1 | Delay | Deadlines may be unable to be met due to low morale, motivation or team members falling sick (& having to take Medical Certificate (MC)). | People Risk | Unrealistic deadlines, COVID-19 clusters, cold weather | Poor planning from higher management, large COVID-19 clusters forming in society, monsoon season | Ensure that the timeline is properly discussed and agreed by the team and client, welfare packs when work gets hectic and ensuring we have backup manpower from other project teams in the company | Jethro Phuah | Medium | High | Open
2 | 2 | Cost | Cost estimation error, leading to a larger than expected cost. | Financial Risk | Underestimated amount of manpower and resources required. | No proper budget plan formulated, did not do enough research to know market rates, spending too much on resources which are not directly impacting project (such as on office rental, transportation) | Have a proper budget and ensure every penny is accounted for, project manager should be tracking expenses and forecast cost at completion, making adjustments when necessary. | Lam Zhi Fah | Medium | High | Closed
3 | 3 | Competition | The team rolls out the project later than competitors. This may lead to competitors acquiring a large portion of market share and establishing themselves as market leaders already. This makes it very difficult for the team to penetrate the market after they have already established themselves. | Market Risk | Not enough market research, the team does not adhere strictly to deadlines | Competitors start getting ready for a launch, rumors start circulating, team morale is low | Conduct sufficient market research, ensure timeline is properly planned and realistic | Shaun Ong | Low | Medium | Open

## Data Validation
Category | Risk Owners | Probability | Status
Market Risk | Jethro Phuah | High | Open
Financial Risk | Alicia Chua | Medium | Close-Diverted
Technology Risk | Ernest Ang | Low | Closed
People Risk | Lam Zhi Fah |  | Pending Closed
Structure/Process Risk | Ong Sim Hao |  | Realised
Shannon Tan
Shaun Ong