## CMMI-Checklist-v1.3
Capability Maturity Model Integration Checklist for Maturity Level 2
Level | Process | Goal | Practice | Subpractice | Work Product | Concept | Detailed | Modular | Info Map | Usable | Evidence | Total
1 - Initial | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 - Managed | 7 | 15 | 54 | 231 | 231 | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1 - Initial | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2- Managed | Requirements Management (REQM) | Manage Requirements | Understand Requirements | Establish criteria for distinguishing appropriate requirements providers | Lists of criteria for distinguishing appropriate requirements providers | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Establish objective criteria for the evaluation and acceptance of requirements | Criteria for evaluation and acceptance of requirements | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Analyze requirements to ensure that established criteria are met | Results of analyses against criteria | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Reach an understanding of requirements with requirements providers so that project participants can commit to them | A set of approved requirements | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Obtain Commitment to Requirements | Assess the impact of requirements on existing commitments | Requirements impact assessments | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Negotiate and record commitments | Documented commitments to requirements and requirements changes | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Manage Requirements Changes | Document all requirements and requirements changes that are given to or generated by the project | Requirements change requests | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Maintain a requirements change history, including the rationale for changes | Requirements change impact reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Evaluate the impact of requirement changes from the standpoint of relevant stakeholders | Requirements status | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Make requirements and change data available to the project | Requirements database | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Maintain Bidirectional Traceability of Requirements | Maintain requirements traceability to ensure that the source of lower level (i.e., derived) requirements is documented | Requirements traceability matrix | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Maintain requirements traceability from a requirement to its derived requirements and allocation to work products | Requirements tracking system | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Generate a requirements traceability matrix | Requirements traceability report | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Ensure Alignment Between Project Work and Requirements | Review project plans, activities, and work products for consistency with requirements and changes made to them | Documentation of inconsistencies between requirements and project plans and work products, including sources and conditions | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify the source of the inconsistency (if any) | Sources of inconsistency | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify any changes that should be made to plans and work products resulting from changes to the requirements baseline | Changes to resolve inconsistencies | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Initiate any necessary corrective actions | Corrective actions | 1 | 2 | 4 | 8 | 16 | 32 | 100%
| Project Planning (PP) | Establish Estimates | Estimate the Scope of the Project | Develop a WBS | WBS | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Define the work packages in sufficient detail so that estimates of project tasks, responsibilities, and schedule can be specified | Task descriptions | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify products and product components to be externally acquired | Product and component list | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify work products to be reused | Reusable work product list | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Establish Estimates of Work Product and Task Attributes | Determine the technical approach for the project | Technical approach | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Use appropriate methods to determine the attributes of the work products and tasks to be used to estimate resource requirements | Estimating models and inputs | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Estimate the attributes of work products and tasks | Attribute estimates | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Develop Project Lifecycle Phases | Develop life cycle phases for each project | Project lifecycle phases | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Estimate Effort and Cost | Collect models or historical data to be used to transform the attributes of work products and tasks into estimates of labor hours and costs | Estimating models and historical data | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Include supporting infrastructure needs when estimating effort and cost | Supporting infrastructure needs | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Estimate effort and cost using models, historical data, or a combination of both | Project effort and cost estimates | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  | Develop a Project Plan | Establish the Budget and Schedule | Identify major milestones | Project milestones | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify schedule assumptions | Project assumptions | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify constraints | Project constraints | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify task dependencies | Schedule dependencies | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Establish and maintain the budget and schedule | Project budget and schedule | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Establish corrective action criteria | Corrective action criteria | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Identify Project Risks | Identify risks | Identified risks | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Document risks | Risk impacts and probability of occurrence | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Review and obtain agreement with relevant stakeholders on the completeness and correctness of documented risks | Risk agreements | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Revise risks as appropriate | Revised risks | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Plan Data Management | Establish requirements and procedures to ensure privacy and the security of data | Privacy and security requirements and procedures | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Establish a mechanism to archive data and to access archived data | Mechanisms for data retrieval, reproduction, and distribution | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Determine the project data to be identified, collected, and distributed | List of project data to be collected | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Determine the requirements for providing access to and distribution of data to relevant stakeholders | Lists of data requirements for acquirers and suppliers | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Decide which project data and plans require version control or other levels of configuration control and establish mechanisms to ensure project data are controlled | Version and configuration control requirements and mechanisms | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Plan the Project’s Resources | Determine process requirements | Process and workflow definitions and diagrams | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Determine communication requirements | Status reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Determine staffing requirements | Staffing requirements based on project size and scope | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Determine facility, equipment, and component requirements | Critical facilities and equipment list | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Determine other continuing resource requirements | Project administration requirements list | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Plan Needed Knowledge and Skills | Identify the knowledge and skills needed to perform the project | Inventory of skill needs | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Assess the knowledge and skills available | Databases (e.g., skills, training, etc.) | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Select mechanisms for providing needed knowledge and skills | Training plans | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Incorporate selected mechanisms into the project plan | Staffing and new hire plans | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Plan Stakeholder Involvement | Develop stakeholder involvement plan | Stakeholder involvement plan | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Establish the Project Plan | Develop overall project plan | Overall project plan | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  | Obtain Commitment to the Plan | Review Plans That Affect the Project | Review interrelated plans that affect the project | Record of the reviews of plans that affect the project | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Reconcile Work and Resource Levels | Revise methods and estimating parameters when necessary | Revised methods and corresponding estimating parameters (e.g., better tools, the use of off-the-shelf components) | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Renegotiate budgets when necessary | Renegotiated budgets | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Revise schedules when necessary | Revised schedules | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Revise requirements when necessary | Revised requirements list | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Renegotiate stakeholder agreements when necessary | Renegotiated stakeholder agreements | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Obtain Plan Commitment | Identify needed support and negotiate commitments with relevant stakeholders. | Documented requests for commitments | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Document all organizational commitments, both full and provisional, ensuring the appropriate level of signatories | Documented commitments | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Review internal commitments with senior management as appropriate | Record of reviewing internal commitments | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Review external commitments with senior management as appropriate | Record of reviewing external commitments | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify commitments regarding interfaces between project elements and other projects and organizational units so that these commitments can be monitored | Commitments regarding interfaces | 1 | 2 | 4 | 8 | 16 | 32 | 100%
| Project Monitoring and Control (PMC) | Monitor the Project Against the Plan | Monitor Project Planning Parameters | Monitor progress against the schedule | Schedule performance reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Monitor the project’s costs and expended effort | Cost performance reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Monitor the attributes of work products and tasks | Records of project performance | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Monitor resources provided and used | Resource consumption reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Monitor the knowledge and skills of project staff | Staff knowledge and skill reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Document significant deviations in project planning parameters | Records of significant deviations | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Monitor Commitments | Regularly review commitments (both external and internal) | Records of prior commitments | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify commitments that have not been satisfied or are at significant risk of not being satisfied | Status of commitments | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Document the results of commitment reviews | Records of commitment reviews | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Monitor Project Risks | Periodically review the documentation of risks in the context of the project’s current status and circumstances | Risk management documentation | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Revise the documentation of risks as additional information becomes available | Updated risk documentation | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Communicate the risk status to relevant stakeholders | Records of project risk monitoring | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Monitor Data Management | Periodically review data management activities against their description in the project plan | Data management activity status | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify and document significant issues and their impacts | Data management issues | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Document results of data management activity reviews | Records of data management | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Monitor Stakeholder Involvement | Periodically review the status of stakeholder involvement | Stakeholder involvement reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify and document significant issues and their impacts | Stakeholder involvement issues | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Document the results of stakeholder involvement status reviews | Records of stakeholder involvement | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Conduct Progress Reviews | Regularly communicate status on assigned activities and work products to relevant stakeholders | Status on assigned activities and work products | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Review the results of collecting and analyzing measures for controlling the project | Collected and analyzed measures | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify and document significant issues and deviations from the plan | Issues and deviations from the plan | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Document change requests and problems identified in work products and processes | Documented change requests | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Document the results of reviews | Documented project review results | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Track change requests and problem reports to closure | Change request and problem report status | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Conduct Milestone Reviews | Conduct milestone reviews with relevant stakeholders at meaningful points in the project’s schedule, such as the completion of selected phases | Milestone review records | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Review commitments, the plan, status, and risks of the project | Milestone review data | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify and document significant issues and their impacts | Milestone issues and impacts | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Document results of the review, action items, and decisions | Documented milestone review results | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Track action items to closure | Milestone action item status | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  | Manage Corrective Action to Closure | Analyze Issues | Gather issues for analysis | List of issues requiring corrective actions | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Analyze issues to determine the need for corrective action | Analysis of issues for corrective action | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Take Corrective Action | Determine and document the appropriate actions needed to address identified issues | Corrective action plans | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Review and get agreement with relevant stakeholders on the actions to be taken | Stakeholder agreement on corrective actions | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Negotiate changes to internal and external commitments | Changes to internal and external commitments | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Manage Corrective Actions | Monitor corrective actions for their completion | Corrective action results | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Analyze results of corrective actions to determine the effectiveness of the corrective actions | Analysis of corrective actions | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Determine and document appropriate actions to correct deviations from planned results from performing corrective actions | Actions for deviations from corrective actions | 1 | 2 | 4 | 8 | 16 | 32 | 100%
| Supplier Agreement Management (SAM) | Establish Supplier Agreements | Determine Acquisition Type | Determine type of acquisition | List of the acquisition types that will be used for all products and product components to be acquired | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Select Suppliers | Establish and document criteria for evaluating potential suppliers | Trade study or other record of evaluation criteria, advantages and disadvantages of candidate suppliers, and rationale for selection of suppliers | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify potential suppliers and distribute solicitation material and requirements to them | List of candidate suppliers, solicitation materials, and requirements | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Evaluate proposals according to evaluation criteria | Supplier proposals and market studies | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Evaluate risks associated with each proposed supplier | Supplier risks | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Evaluate proposed suppliers’ abilities to perform the work | Supplier evaluations | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Select the supplier | Preferred supplier list | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Establish Supplier Agreements | Revise the requirements (e.g., product requirements, service level requirements) to be fulfilled by the supplier to reflect negotiations with the supplier when necessary | Supplier requirement revisions | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Document what the project will provide to the supplier | Requirements for customer supplied items | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Document the supplier agreement | Statements of work, contracts, memoranda of agreement, and licensing agreement | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Periodically review the supplier agreement to ensure it accurately reflects the project’s relationship with the supplier and current risks and market conditions | Records of reviewing supplier agreements | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Ensure that all parties to the supplier agreement understand and agree to all requirements before implementing the agreement or any changes | Supplier agreement commitments | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Revise the supplier agreement as necessary to reflect changes to the supplier’s processes or work products | Supplier agreement revisions | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Revise the project’s plans and commitments, including changes to the project’s processes or work products, as necessary to reflect the supplier agreement | Project plan and commitment revisions | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  | Satisfy Supplier Agreements | Execute the Supplier Agreement | Monitor supplier progress and performance (e.g., schedule, effort, cost, technical performance) as defined in the supplier agreement | Supplier progress reports and performance measures | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Select, monitor, and analyze processes used by the supplier as defined in the supplier agreement | Supplier process performance reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Select and evaluate work products from the supplier as defined in the supplier agreement | Supplier review materials and reports, and product and documentation deliveries | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Conduct reviews with the supplier as specified in the supplier agreement | Records of supplier reviews | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Conduct technical reviews with the supplier as defined in the supplier agreement | Records of technical supplier reviews | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Conduct management reviews with the supplier as defined in the supplier agreement | Records of management supplier reviews | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Use the results of reviews to improve the supplier’s performance and to establish and nurture long-term relationships with preferred suppliers | Supplier performance improvement action plans | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Monitor risks involving the supplier and take corrective action as necessary | Risks, action items, and corrective actions tracked to closure | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Accept the Acquired Product | Define the acceptance procedures | Acceptance procedures | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Review and obtain agreement from relevant stakeholders on the acceptance procedures before the acceptance review or test | Agreements on acceptance procedures | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Verify that the acquired products satisfy their requirements | Results of reviewing acquired products | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Confirm that the nontechnical commitments associated with the acquired work product are satisfied | Results of reviewing non-technical commitments | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Document the results of the acceptance review or test | Acceptance reviews or test results | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Establish an action plan and obtain supplier agreement to take action to correct acquired work products that do not pass their acceptance review or test | Corrective action plans | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify, document, and track action items to closure. | Discrepancy reports and action items | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Ensure Transition of Products | Ensure that facilities exist to receive, store, integrate, and maintain the acquired products as appropriate | Transition plans | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Ensure that appropriate training is provided for those who are involved in receiving, storing, integrating, and maintaining acquired products | Training reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Ensure that acquired products are stored, distributed, and integrated according to the terms and conditions specified in the supplier agreement or license | Support and maintenance reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
| Measurement and Analysis (MA) | Align Measurement and Analysis Activities | Establish Measurement Objectives | Document information needs and objectives | Measurement objectives | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Prioritize information needs and objectives | Measurement priorities | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Document, review, and update measurement objectives | Results of documenting and reviewing measurement objectives | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Provide feedback for refining and clarifying information needs and objectives as necessary | Feedback on measurement objectives | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Maintain traceability of measurement objectives to identified information needs and objectives | Traceability of measurement objectives | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Specify Measures | Identify candidate measures based on documented measurement objectives | List of candidate measures | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Maintain traceability of measures to measurement objectives | Traceability of measures to objectives | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify existing measures that already address measurement objectives | List of existing measures | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Specify operational definitions for measures. Operational definitions are stated in precise and unambiguous terms | Specifications of base and derived measures | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Prioritize, review, and update measures | Updated measures | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Specify Data Collection and Storage Procedures | Identify existing sources of data that are generated from current work products, processes, or transactions | Existing sources of data | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify measures for which data are needed but are not currently available | Measurement data not currently available | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Specify how to collect and store the data for each required measure | Data collection and storage procedures | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Create data collection mechanisms and process guidance | Data collection mechanisms and guidance | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Support automatic collection of data as appropriate and feasible | Data collection tools | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Prioritize, review, and update data collection and storage procedures | Prioritized data collection and storage procedures | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Update measures and measurement objectives as necessary | Updated measures and measurement objectives | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Specify Analysis Procedures | Specify and prioritize the analyses to be conducted and the reports to be prepared | Prioritized analyses and reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Select appropriate data analysis methods and tools | Data analysis tools | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Specify administrative procedures for analyzing data and communicating results | Analysis specifications and procedures | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Review and update the proposed content and format of specified analyses and reports | Updated analysis and report content and reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Update measures and measurement objectives as necessary | Updated measures and measurement objectives | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Specify criteria for evaluating the utility of analysis results and for evaluating the conduct of measurement and analysis activities | Criteria for evaluating analyses | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  | Provide Measurement Results | Obtain Measurement Data | Obtain data for base measures | Base measurement data sets | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Generate data for derived measures | Derived measurement data sets | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Perform data integrity checks as close to the source of data as possible | Results of data integrity tests | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Analyze Measurement Data | Conduct initial analyses, interpret results, and draw preliminary conclusions | Analysis results and draft reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Conduct additional measurement and analysis as necessary and prepare results for presentation | Additional measurement and analysis results | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Review initial results with relevant stakeholders | Records of reviewing initial results | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Refine criteria for future analyses | Refined criteria for future analyses | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Store Data and Results | Review data to ensure their completeness, integrity, accuracy, and currency | Data to be reviewed | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Store data according to data storage procedures | Stored data inventory | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Make stored contents available for use only to appropriate groups and staff members | Access to stored data inventory | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Prevent stored information from being used inappropriately | Access controls for stored data inventory | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Communicate Results | Keep relevant stakeholders informed of measurement results in a timely manner | Delivered reports and related analysis results | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Assist relevant stakeholders in understanding results | Contextual information or guidance to help interpret analysis results | 1 | 2 | 4 | 8 | 16 | 32 | 100%
| Process and Product Quality Assurance (PPQA) | Objectively Evaluate Processes and Work Products | Objectively Evaluate Processes | Promote an environment (created as part of project management) that encourages staff participation in identifying and reporting quality issues | Policy for identifying and reporting quality issues | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Establish and maintain clearly stated criteria for evaluations | Criteria for evaluations | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Use the stated criteria to evaluate selected performed processes for adherence to process descriptions, standards, and procedures | Evaluation reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify each noncompliance found during the evaluation | Noncompliance reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify lessons learned that could improve processes | Lessons learned and corrective actions | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Objectively Evaluate Work Products | Select work products to be evaluated based on documented sampling criteria if sampling is used | List of work products to be evaluated | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Establish and maintain clearly stated criteria for the evaluation of selected work products | Criteria for evaluating work products | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Use the stated criteria during evaluations of selected work products | Evaluation reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Evaluate selected work products at selected times | Schedule for evaluating work products | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify each case of noncompliance found during evaluations | Noncompliance reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify lessons learned that could improve processes | Lessons learned and corrective actions | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  | Provide Objective Insight | Communicate and Resolve Noncompliance Issues | Resolve each noncompliance with the appropriate members of the staff if possible | Results of resolving noncompliances | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Document noncompliance issues when they cannot be resolved in the project | List of noncompliance issues | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Escalate noncompliance issues that cannot be resolved in the project to the appropriate level of management designated to receive and act on noncompliance issues | List of unresolvable noncompliance issues | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Analyze noncompliance issues to see if there are quality trends that can be identified and addressed | Analysis of noncompliance issues | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Ensure that relevant stakeholders are aware of results of evaluations and quality trends in a timely manner | Evaluation reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Periodically review open noncompliance issues and trends with the manager designated to receive and act on noncompliance issues | Quality trends | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Track noncompliance issues to resolution | Corrective action reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Establish Records | Record process and product quality assurance activities in sufficient detail so that status and results are known | Status reports of corrective actions and evaluation logs | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Revise the status and history of quality assurance activities as necessary | Reports of quality trends and quality assurance reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
| Configuration Management (CM) | Establish Baselines | Identify Configuration Items | Select configuration items and work products that compose them based on documented criteria | Selected configuration items | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Assign unique identifiers to configuration items | List of unique identifiers | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Specify the important characteristics of each configuration item | List of important characteristics | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Specify when each configuration item is placed under configuration management | Identified configuration items | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify the owner responsible for each configuration item | Configuration item owner | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Specify relationships among configuration items | Configuration item relationships | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Establish a Configuration Management System | Establish a mechanism to manage multiple levels of control | Configuration management system with controlled work products | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Provide access control to ensure authorized access to the configuration management system | Configuration management system access control procedures | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Store and retrieve configuration items in a configuration management system | Change request database | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Share and transfer configuration items between control levels in the configuration management system | Shared configuration items | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Store and recover archived versions of configuration items | Archived versions of configuration items | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Store, update, and retrieve configuration management records | Configuration management records | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Create configuration management reports from the configuration management system | Configuration management reports | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Preserve the contents of the configuration management system | Contents of configuration management system | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Revise the configuration management structure as necessary | Revised configuration management structure | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Create or Release Baselines | Obtain authorization from the CCB before creating or releasing baselines of configuration items | Authorization to create and release baselines | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Create or release baselines only from configuration items in the configuration management system | Baselines | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Document the set of configuration items that are contained in a baseline | Description of baselines | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Make the current set of baselines readily available | List of available baselines | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  | Track and Control Changes | Track Change Requests | Initiate and record change requests in the change request database | Change requests | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Analyze the impact of changes and fixes proposed in change requests | Impacts of changes | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Categorize and prioritize change requests. | Categorized change requests | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Review change requests to be addressed in the next baseline with relevant stakeholders and get their agreement | Reviewed change requests | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Track the status of change requests to closure | Status of change requests | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Control Configuration Items | Control changes to configuration items throughout the life of the product or service. | Revision history of configuration items | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Obtain appropriate authorization before changed configuration items are entered into the configuration management system. | Authorization to change configuration items | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Check in and check out configuration items in the configuration management system for incorporation of changes in a manner that maintains the correctness and integrity of configuration items. | Records of access to configuration items | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Perform reviews to ensure that changes have not caused unintended effects on the baselines (e.g., ensure that changes have not compromised the safety or security of the system) | Results of reviewing baselines | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Record changes to configuration items and reasons for changes as appropriate | Archives of baselines | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  | Establish Integrity | Establish Configuration Management Records | Record configuration management actions in sufficient detail so the content and status of each configuration item is known and previous versions can be recovered | Change request records, change log, and status of configuration items | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Ensure that relevant stakeholders have access to and knowledge of the configuration status of configuration items | Access list to configuration status and items | 1 | 2 | 4 | 8 | 16 | 32 | 100% | C
|  |  |  | Specify the latest version of baselines | Latest versions of baselines | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Identify the version of configuration items that constitute a particular baseline | Versions of configuration items | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Describe differences between successive baselines | Differences between baselines | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Revise the status and history (i.e., changes, other actions) of each configuration item as necessary | Revision history of configuration items | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  | Perform Configuration Audits | Assess the integrity of baselines | Results of assessing baseline integrity | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Confirm that configuration management records correctly identify configuration items | Results of confirming configuration management records | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Review the structure and integrity of items in the configuration management system | Results of confirming configuration management structure | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Confirm the completeness, correctness, and consistency of items in the configuration management system | Results of confirming configuration management completeness | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Confirm compliance with applicable configuration management standards and procedures | Results of confirming configuration management compliance | 1 | 2 | 4 | 8 | 16 | 32 | 100%
|  |  |  | Track action items from the audit to closure | Action items | 1 | 2 | 4 | 8 | 16 | 32 | 100%