## Team Meeting 3
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Member 6 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Jethro Phuah | Lam Zhi Fah | Alicia Chua | Shannon Tan | Shaun Ong | Sim Hao | Ernest Ang
Team member's mood during the this week's meeting: |  |  | Depressed | Sad | Depressed | Depressed | Happy | Neutral | Happy
1 | Complete Change Management Plan | Task Quality Evaluation (After Task Completed) | 9 | 9 | 8 | 8 | 8 | 9 | 8 | 7.7143 | 7.8571 | 2.8571 | Shannon Tan | Alicia Chua | Allocated by Team Leader | Yes | 5 | Neutral | 8.4286
| Estimated Task Priority（0-10） |  | 7 | 9 | 7 | 7 | 8 | 9 | 7
| Estimated Task Difficulty（0-10） |  | 8 | 8 | 9 | 8 | 7 | 7 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 3 | 4 | 3 | 2 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 7 | 9 | 7 | 9 | 8
2 | Complete Release Plan | Task Quality Evaluation (After Task Completed) | 9 | 8 | 9 | 10 | 9 | 9 | 9 | 8.7143 | 9.1429 | 3.8571 | Sim Hao | Jethro Phuah | Allocated by Team Leader | Yes | 3 | Happy | 9
| Estimated Task Priority（0-10） |  | 8 | 9 | 7 | 9 | 9 | 9 | 10
| Estimated Task Difficulty（0-10） |  | 10 | 10 | 10 | 8 | 9 | 8 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 5 | 4 | 4 | 2 | 5
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 7 | 7 | 7 | 7 | 8
3 | Complete Software Configuration Management | Task Quality Evaluation (After Task Completed) | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8.8571 | 8 | 4 | Shaun Ong | Lam Zhi Fah | Through Discussion | Yes | 4 | Happy | 8
| Estimated Task Priority（0-10） |  | 10 | 9 | 8 | 9 | 8 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 8 | 7 | 8 | 9 | 8 | 8 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 4 | 5 | 3 | 4 | 5 | 3
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 8 | 9 | 8 | 8 | 9
4 | Complete Design Report on Software Maintainability | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 9 | 9 | 10 | 8.7143 | 4.2857 | Ernest Ang | Sim Hao, Shaun Ong | Through Discussion | Yes | 5 | Happy | 9.7143
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 9 | 9 | 9 | 8 | 8 | 9 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 5 | 5 | 4 | 4 | 5
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 8 | 7 | 7 | 8 | 8
5 | Continue development of Admin dashboard | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 10 | 8.7143 | 10 | Jethro Phuah | Sim Hao, Shaun, Zhi Fah, Shannon, Alicia | Through Discussion | Yes | 10 | Happy | 9.8571
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 9 | 9 | 9 | 8 | 8 | 9 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 9 | 10 | 11 | 9 | 10 | 11 | 10
| Team Member's Confidence about the Task (0-10) |  | 10 | 8 | 8 | 9 | 9 | 8 | 9
6 | Continue development of HangOut app | Task Quality Evaluation (After Task Completed) | 9 | 9 | 10 | 10 | 8 | 9 | 10 | 10 | 9 | 10 | Jethro Phuah | Sim Hao, Shaun, Zhi Fah, Shannon, Alicia | Through Discussion | Yes | 10 | Happy | 9.2857
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 9 | 9 | 10 | 9 | 8 | 9 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 10 | 10 | 10 | 11 | 9 | 11 | 9
| Team Member's Confidence about the Task (0-10) |  | 7 | 7 | 6 | 7 | 7 | 8 | 9